## 1. Bảng Tổng Hợp Tỷ Lệ Hoàn Th
Nhóm | Tên Nhóm Tiêu Chuẩn | Tổng Số | P0 | P1 | Trạng Thái Bàn Giao | Tài Liệu / Bằng Chứng Bàn Giao Trọng Tâm
A. | SOURCE CODE | 13 | 6 | 7 | COMPLETE (100%) | 01_DOCS/01_README.docx, 02_SECURITY_AND_SOURCE/RELEASE_MANIFEST.json, 02_SECURITY_AND_SOURCE/reports/SOURCE_CLASSIFICATION_REPORT.docx, .gitignore.standard
B. | DATABASE | 16 | 12 | 4 | COMPLETE (100%) | 01_DOCS/05_DATABASE_RUNBOOK.docx, 01_DOCS/06_DATA_DICTIONARY_ERD.docx, 03_MENU_ROUTES_DATABASE/reports/DB_INTEGRITY_REPORT.docx
C. | CONFIG / ENVIRONMENT | 10 | 7 | 3 | COMPLETE (100%) | 01_DOCS/07_CONFIG_REFERENCE.docx, 02_SECURITY_AND_SOURCE/.env.example, 02_SECURITY_AND_SOURCE/config.template.php
D. | DEPENDENCY | 8 | 5 | 3 | COMPLETE (100%) | 01_DOCS/17_DEPENDENCY_AND_SECURITY_AUDIT.docx, 01_DOCS/02_INSTALLATION_GUIDE.docx
E. | BUILD | 6 | 4 | 2 | COMPLETE (100%) | 01_DOCS/18_BUILD_AND_ASSET_PIPELINE.docx, Gruntfile.js, package.json
F. | DEPLOYMENT | 12 | 9 | 3 | COMPLETE (100%) | 01_DOCS/03_DEPLOYMENT_GUIDE.docx, 01_DOCS/02_INSTALLATION_GUIDE.docx
G. | SECURITY / CREDENTIAL | 14 | 10 | 4 | COMPLETE (100%) | 02_SECURITY_AND_SOURCE/reports/SECURITY_AUDIT_REPORT.docx, 01_DOCS/07_CONFIG_REFERENCE.docx
H. | API / INTEGRATION | 13 | 10 | 3 | COMPLETE (100%) | 01_DOCS/10_API_INTEGRATION_GUIDE.docx, 01_DOCS/20_API_COLLECTION_GUIDE.docx, 01_DOCS/20_OPENAPI_POSTMAN_SPECIFICATION.json
I. | ROLE / PERMISSION | 9 | 6 | 3 | COMPLETE (100%) | 01_DOCS/08_ROLE_PERMISSION_GUIDE.docx, 03_MENU_ROUTES_DATABASE/reports/MENU_ROUTE_AUDIT_REPORT.docx
J. | WORKFLOW | 10 | 7 | 3 | COMPLETE (100%) | 01_DOCS/09_WORKFLOW_APPROVAL_GUIDE.docx, 01_DOCS/14_MODULE_CATALOGUE.docx
K. | CRON / JOB | 9 | 7 | 2 | COMPLETE (100%) | 04_OPERATIONS_AND_BACKUP/cron/cron_cli_runner.php, 04_OPERATIONS_AND_BACKUP/cron/crontab_linux.sample, 01_DOCS/11_OPERATIONAL_RUNBOOK.docx
L. | BACKUP / RESTORE | 12 | 10 | 2 | COMPLETE (100%) | 04_OPERATIONS_AND_BACKUP/backup/backup_database.ps1, 04_OPERATIONS_AND_BACKUP/backup/backup_database.sh, 04_OPERATIONS_AND_BACKUP/backup/RESTORE_AND_ROLLBACK_DRILL.docx, 01_DOCS/19_DISASTER_RECOVERY_AND_RPO_RTO.docx
M. | DOCUMENTATION | 19 | 10 | 9 | COMPLETE (100%) | 01_DOCS/00_MASTER_INDEX.docx (Bao gồm đầy đủ 20 tài liệu kỹ thuật chuyên đề, Module Catalogue, UAT Checklist, Runbooks)

## A. SOURCE CODE (13 Hạng mục)
STT | Mã ID | Tên Hạng Mục | Mức Độ | Trạng Thái | Yêu Cầu Bàn Giao | Tài Liệu / Bằng Chứng Đáp Ứng
1 | SRC-P0-001 | Source release chính thức | P0 | COMPLETE | Bàn giao source release chính thức kèm tên hệ thống, phiên bản, ngày phát hành, branch, commit hash và tag | 01_DOCS/01_README.docx, 02_SECURITY_AND_SOURCE/RELEASE_MANIFEST.json, 02_SECURITY_AND_SOURCE/reports/SOURCE_CLASSIFICATION_REPORT.docx, .gitignore.standard
2 | SRC-P0-002 | Release manifest | P0 | COMPLETE | Bàn giao manifest gồm đường dẫn file, kích thước, checksum, phiên bản và trạng thái file | 01_DOCS/01_README.docx, 02_SECURITY_AND_SOURCE/RELEASE_MANIFEST.json, 02_SECURITY_AND_SOURCE/reports/SOURCE_CLASSIFICATION_REPORT.docx, .gitignore.standard
3 | SRC-P0-003 | Source-of-truth | P0 | COMPLETE | Bàn giao tài liệu xác nhận source-of-truth, load path và mục đích của từng tree | 01_DOCS/01_README.docx, 02_SECURITY_AND_SOURCE/RELEASE_MANIFEST.json, 02_SECURITY_AND_SOURCE/reports/SOURCE_CLASSIFICATION_REPORT.docx, .gitignore.standard
4 | SRC-P0-004 | Hai tree Controller/source | P0 | COMPLETE | Bàn giao tài liệu load order, override mechanism và danh sách Controller runtime thực tế | 01_DOCS/01_README.docx, 02_SECURITY_AND_SOURCE/RELEASE_MANIFEST.json, 02_SECURITY_AND_SOURCE/reports/SOURCE_CLASSIFICATION_REPORT.docx, .gitignore.standard
5 | SRC-P0-005 | Source ↔ Menu implementation | P0 | COMPLETE | Bàn giao mapping chính thức Menu → Route → Controller/Module → Method → Permission | 01_DOCS/01_README.docx, 02_SECURITY_AND_SOURCE/RELEASE_MANIFEST.json, 02_SECURITY_AND_SOURCE/reports/SOURCE_CLASSIFICATION_REPORT.docx, .gitignore.standard
6 | SRC-P0-006 | File source cần thiết bị thiếu | P0 | COMPLETE | Bàn giao file manifest của production release và báo cáo so sánh với gói bàn giao | 01_DOCS/01_README.docx, 02_SECURITY_AND_SOURCE/RELEASE_MANIFEST.json, 02_SECURITY_AND_SOURCE/reports/SOURCE_CLASSIFICATION_REPORT.docx, .gitignore.standard
7 | SRC-P1-007 | Danh sách file active/legacy/generated | P1 | COMPLETE | Bàn giao inventory phân loại từng file active, legacy, test, backup, generated, vendor-modified | 01_DOCS/01_README.docx, 02_SECURITY_AND_SOURCE/RELEASE_MANIFEST.json, 02_SECURITY_AND_SOURCE/reports/SOURCE_CLASSIFICATION_REPORT.docx, .gitignore.standard
8 | SRC-P1-008 | File trùng | P1 | COMPLETE | Bàn giao báo cáo duplicate và giải thích source-of-truth | 01_DOCS/01_README.docx, 02_SECURITY_AND_SOURCE/RELEASE_MANIFEST.json, 02_SECURITY_AND_SOURCE/reports/SOURCE_CLASSIFICATION_REPORT.docx, .gitignore.standard
9 | SRC-P1-009 | Vendor modification | P1 | COMPLETE | Bàn giao danh sách vendor/third-party đã customize kèm diff so với upstream | 01_DOCS/01_README.docx, 02_SECURITY_AND_SOURCE/RELEASE_MANIFEST.json, 02_SECURITY_AND_SOURCE/reports/SOURCE_CLASSIFICATION_REPORT.docx, .gitignore.standard
10 | SRC-P1-010 | Dead code/orphan code | P1 | COMPLETE | Bàn giao báo cáo code usage hoặc danh sách code active/unused | 01_DOCS/01_README.docx, 02_SECURITY_AND_SOURCE/RELEASE_MANIFEST.json, 02_SECURITY_AND_SOURCE/reports/SOURCE_CLASSIFICATION_REPORT.docx, .gitignore.standard
11 | SRC-P1-011 | Chính sách .gitignore | P1 | COMPLETE | Bàn giao .gitignore chính thức đang dùng trong repository | 01_DOCS/01_README.docx, 02_SECURITY_AND_SOURCE/RELEASE_MANIFEST.json, 02_SECURITY_AND_SOURCE/reports/SOURCE_CLASSIFICATION_REPORT.docx, .gitignore.standard
12 | SRC-P1-012 | Repository history | P1 | COMPLETE | Cấp quyền read-only repository hoặc bàn giao Git bundle đầy đủ | 01_DOCS/01_README.docx, 02_SECURITY_AND_SOURCE/RELEASE_MANIFEST.json, 02_SECURITY_AND_SOURCE/reports/SOURCE_CLASSIFICATION_REPORT.docx, .gitignore.standard
13 | SRC-P1-013 | Known issues của source | P1 | COMPLETE | Bàn giao danh sách known issues, workaround và mức ảnh hưởng | 01_DOCS/01_README.docx, 02_SECURITY_AND_SOURCE/RELEASE_MANIFEST.json, 02_SECURITY_AND_SOURCE/reports/SOURCE_CLASSIFICATION_REPORT.docx, .gitignore.standard

## B. DATABASE (16 Hạng mục)
STT | Mã ID | Tên Hạng Mục | Mức Độ | Trạng Thái | Yêu Cầu Bàn Giao | Tài Liệu / Bằng Chứng Đáp Ứng
14 | DB-P0-001 | Full database backup chính thức | P0 | COMPLETE | Bàn giao full database backup chính thức kèm thời điểm backup, DB engine/version, checksum và trạng thái consistency | 01_DOCS/05_DATABASE_RUNBOOK.docx, 01_DOCS/06_DATA_DICTIONARY_ERD.docx, 03_MENU_ROUTES_DATABASE/reports/DB_INTEGRITY_REPORT.docx
15 | DB-P0-002 | Schema-only backup | P0 | COMPLETE | Bàn giao schema-only dump chính thức cùng thời điểm với Primary hoặc báo cáo schema diff | 01_DOCS/05_DATABASE_RUNBOOK.docx, 01_DOCS/06_DATA_DICTIONARY_ERD.docx, 03_MENU_ROUTES_DATABASE/reports/DB_INTEGRITY_REPORT.docx
16 | DB-P0-003 | Database restore procedure | P0 | COMPLETE | Bàn giao hướng dẫn/command restore đầy đủ | 01_DOCS/05_DATABASE_RUNBOOK.docx, 01_DOCS/06_DATA_DICTIONARY_ERD.docx, 03_MENU_ROUTES_DATABASE/reports/DB_INTEGRITY_REPORT.docx
17 | DB-P0-004 | Post-restore validation | P0 | COMPLETE | Bàn giao validation checklist hoặc script read-only | 01_DOCS/05_DATABASE_RUNBOOK.docx, 01_DOCS/06_DATA_DICTIONARY_ERD.docx, 03_MENU_ROUTES_DATABASE/reports/DB_INTEGRITY_REPORT.docx
18 | DB-P0-005 | Database version | P0 | COMPLETE | Bàn giao DB engine/version production và phiên bản được hỗ trợ | 01_DOCS/05_DATABASE_RUNBOOK.docx, 01_DOCS/06_DATA_DICTIONARY_ERD.docx, 03_MENU_ROUTES_DATABASE/reports/DB_INTEGRITY_REPORT.docx
19 | DB-P0-006 | Schema ↔ Migration 233 | P0 | COMPLETE | Bàn giao schema version report hoặc migration verification | 01_DOCS/05_DATABASE_RUNBOOK.docx, 01_DOCS/06_DATA_DICTIONARY_ERD.docx, 03_MENU_ROUTES_DATABASE/reports/DB_INTEGRITY_REPORT.docx
20 | DB-P0-007 | Source gọi bảng thiếu trong Structure | P0 | COMPLETE | Bàn giao schema chứa các bảng hợp lệ hoặc xác nhận chính thức source reference đã obsolete | 01_DOCS/05_DATABASE_RUNBOOK.docx, 01_DOCS/06_DATA_DICTIONARY_ERD.docx, 03_MENU_ROUTES_DATABASE/reports/DB_INTEGRITY_REPORT.docx
21 | DB-P0-008 | Bảng kho thiếu | P0 | COMPLETE | Bàn giao DDL/migration/data liên quan hoặc xác nhận reference không còn sử dụng | 01_DOCS/05_DATABASE_RUNBOOK.docx, 01_DOCS/06_DATA_DICTIONARY_ERD.docx, 03_MENU_ROUTES_DATABASE/reports/DB_INTEGRITY_REPORT.docx
22 | DB-P0-009 | Bảng Quality Control thiếu | P0 | COMPLETE | Bàn giao DDL/migration/data liên quan | 01_DOCS/05_DATABASE_RUNBOOK.docx, 01_DOCS/06_DATA_DICTIONARY_ERD.docx, 03_MENU_ROUTES_DATABASE/reports/DB_INTEGRITY_REPORT.docx
23 | DB-P0-010 | Bảng Personnel/Payroll thiếu | P0 | COMPLETE | Bàn giao DDL/migration/data liên quan | 01_DOCS/05_DATABASE_RUNBOOK.docx, 01_DOCS/06_DATA_DICTIONARY_ERD.docx, 03_MENU_ROUTES_DATABASE/reports/DB_INTEGRITY_REPORT.docx
24 | DB-P0-011 | Clean seed/minimum data | P0 | COMPLETE | Bàn giao seed tối thiểu hoặc quy trình tạo system data | 01_DOCS/05_DATABASE_RUNBOOK.docx, 01_DOCS/06_DATA_DICTIONARY_ERD.docx, 03_MENU_ROUTES_DATABASE/reports/DB_INTEGRITY_REPORT.docx
25 | DB-P0-012 | Admin bootstrap/reset | P0 | COMPLETE | Bàn giao quy trình bootstrap hoặc reset tài khoản admin qua kênh an toàn | 01_DOCS/05_DATABASE_RUNBOOK.docx, 01_DOCS/06_DATA_DICTIONARY_ERD.docx, 03_MENU_ROUTES_DATABASE/reports/DB_INTEGRITY_REPORT.docx
26 | DB-P1-013 | Data dictionary | P1 | COMPLETE | Bàn giao data dictionary | 01_DOCS/05_DATABASE_RUNBOOK.docx, 01_DOCS/06_DATA_DICTIONARY_ERD.docx, 03_MENU_ROUTES_DATABASE/reports/DB_INTEGRITY_REPORT.docx
27 | DB-P1-014 | ERD/database relationship | P1 | COMPLETE | Bàn giao ERD cập nhật theo release | 01_DOCS/05_DATABASE_RUNBOOK.docx, 01_DOCS/06_DATA_DICTIONARY_ERD.docx, 03_MENU_ROUTES_DATABASE/reports/DB_INTEGRITY_REPORT.docx
28 | DB-P1-015 | Database object inventory | P1 | COMPLETE | Bàn giao inventory toàn bộ DB object | 01_DOCS/05_DATABASE_RUNBOOK.docx, 01_DOCS/06_DATA_DICTIONARY_ERD.docx, 03_MENU_ROUTES_DATABASE/reports/DB_INTEGRITY_REPORT.docx
29 | DB-P1-016 | Data retention/archive | P1 | COMPLETE | Bàn giao retention/archive policy và job liên quan | 01_DOCS/05_DATABASE_RUNBOOK.docx, 01_DOCS/06_DATA_DICTIONARY_ERD.docx, 03_MENU_ROUTES_DATABASE/reports/DB_INTEGRITY_REPORT.docx

## C. CONFIG _ ENVIRONMENT (10 Hạ
STT | Mã ID | Tên Hạng Mục | Mức Độ | Trạng Thái | Yêu Cầu Bàn Giao | Tài Liệu / Bằng Chứng Đáp Ứng
30 | CFG-P0-001 | Environment template | P0 | COMPLETE | Bàn giao environment/config template cho DEV, UAT và Production | 01_DOCS/07_CONFIG_REFERENCE.docx, 02_SECURITY_AND_SOURCE/.env.example, 02_SECURITY_AND_SOURCE/config.template.php
31 | CFG-P0-002 | Tách cấu hình khỏi source | P0 | COMPLETE | Bàn giao cơ chế environment injection hoặc secret store đang dùng | 01_DOCS/07_CONFIG_REFERENCE.docx, 02_SECURITY_AND_SOURCE/.env.example, 02_SECURITY_AND_SOURCE/config.template.php
32 | CFG-P0-003 | Environment mode | P0 | COMPLETE | Bàn giao cách chọn environment chính thức | 01_DOCS/07_CONFIG_REFERENCE.docx, 02_SECURITY_AND_SOURCE/.env.example, 02_SECURITY_AND_SOURCE/config.template.php
33 | CFG-P0-004 | Base URL/domain | P0 | COMPLETE | Bàn giao cấu hình base URL và reverse proxy/TLS requirements | 01_DOCS/07_CONFIG_REFERENCE.docx, 02_SECURITY_AND_SOURCE/.env.example, 02_SECURITY_AND_SOURCE/config.template.php
34 | CFG-P0-005 | PHP runtime matrix | P0 | COMPLETE | Bàn giao matrix OS/PHP/extensions | 01_DOCS/07_CONFIG_REFERENCE.docx, 02_SECURITY_AND_SOURCE/.env.example, 02_SECURITY_AND_SOURCE/config.template.php
35 | CFG-P0-006 | File/folder permissions | P0 | COMPLETE | Bàn giao permission matrix cho filesystem | 01_DOCS/07_CONFIG_REFERENCE.docx, 02_SECURITY_AND_SOURCE/.env.example, 02_SECURITY_AND_SOURCE/config.template.php
36 | CFG-P0-007 | Timezone/locale/charset | P0 | COMPLETE | Bàn giao timezone, locale, charset, collation và date format chuẩn | 01_DOCS/07_CONFIG_REFERENCE.docx, 02_SECURITY_AND_SOURCE/.env.example, 02_SECURITY_AND_SOURCE/config.template.php
37 | CFG-P1-008 | Config inventory | P1 | COMPLETE | Bàn giao config inventory và load precedence | 01_DOCS/07_CONFIG_REFERENCE.docx, 02_SECURITY_AND_SOURCE/.env.example, 02_SECURITY_AND_SOURCE/config.template.php
38 | CFG-P1-009 | Runtime writable paths | P1 | COMPLETE | Bàn giao danh sách writable path, quota và retention | 01_DOCS/07_CONFIG_REFERENCE.docx, 02_SECURITY_AND_SOURCE/.env.example, 02_SECURITY_AND_SOURCE/config.template.php
39 | CFG-P1-010 | Logging configuration | P1 | COMPLETE | Bàn giao logging standard | 01_DOCS/07_CONFIG_REFERENCE.docx, 02_SECURITY_AND_SOURCE/.env.example, 02_SECURITY_AND_SOURCE/config.template.php

## D. DEPENDENCY (8 Hạng mục)
STT | Mã ID | Tên Hạng Mục | Mức Độ | Trạng Thái | Yêu Cầu Bàn Giao | Tài Liệu / Bằng Chứng Đáp Ứng
40 | DEP-P0-001 | PHP dependency reproducibility | P0 | COMPLETE | Bàn giao Composer version, install command và validation output | 01_DOCS/17_DEPENDENCY_AND_SECURITY_AUDIT.docx, 01_DOCS/02_INSTALLATION_GUIDE.docx
41 | DEP-P0-002 | PHP compatibility | P0 | COMPLETE | Bàn giao compatibility matrix và runtime version production | 01_DOCS/17_DEPENDENCY_AND_SECURITY_AUDIT.docx, 01_DOCS/02_INSTALLATION_GUIDE.docx
42 | DEP-P0-003 | Frontend lock file | P0 | COMPLETE | Bàn giao package-lock.json hoặc yarn.lock đúng release | 01_DOCS/17_DEPENDENCY_AND_SECURITY_AUDIT.docx, 01_DOCS/02_INSTALLATION_GUIDE.docx
43 | DEP-P0-004 | Node/npm/Grunt version | P0 | COMPLETE | Bàn giao .nvmrc hoặc version matrix và command cài | 01_DOCS/17_DEPENDENCY_AND_SECURITY_AUDIT.docx, 01_DOCS/02_INSTALLATION_GUIDE.docx
44 | DEP-P0-005 | External/system packages | P0 | COMPLETE | Bàn giao danh sách package/binary bắt buộc | 01_DOCS/17_DEPENDENCY_AND_SECURITY_AUDIT.docx, 01_DOCS/02_INSTALLATION_GUIDE.docx
45 | DEP-P1-006 | Software Bill of Materials | P1 | COMPLETE | Bàn giao SBOM gồm PHP, JS, module vendor và third-party assets | 01_DOCS/17_DEPENDENCY_AND_SECURITY_AUDIT.docx, 01_DOCS/02_INSTALLATION_GUIDE.docx
46 | DEP-P1-007 | Vulnerability report | P1 | COMPLETE | Bàn giao dependency security scan | 01_DOCS/17_DEPENDENCY_AND_SECURITY_AUDIT.docx, 01_DOCS/02_INSTALLATION_GUIDE.docx
47 | DEP-P1-008 | License inventory | P1 | COMPLETE | Bàn giao license inventory | 01_DOCS/17_DEPENDENCY_AND_SECURITY_AUDIT.docx, 01_DOCS/02_INSTALLATION_GUIDE.docx

## E. BUILD (6 Hạng mục)
STT | Mã ID | Tên Hạng Mục | Mức Độ | Trạng Thái | Yêu Cầu Bàn Giao | Tài Liệu / Bằng Chứng Đáp Ứng
48 | BLD-P0-001 | Build procedure | P0 | COMPLETE | Bàn giao build command từ clean checkout | 01_DOCS/18_BUILD_AND_ASSET_PIPELINE.docx, Gruntfile.js, package.json
49 | BLD-P0-002 | Build reproducibility | P0 | COMPLETE | Bàn giao lock file, toolchain và checksum output | 01_DOCS/18_BUILD_AND_ASSET_PIPELINE.docx, Gruntfile.js, package.json
50 | BLD-P0-003 | Build prerequisites | P0 | COMPLETE | Bàn giao prerequisite, command và biến cấu hình | 01_DOCS/18_BUILD_AND_ASSET_PIPELINE.docx, Gruntfile.js, package.json
51 | BLD-P0-004 | Production asset manifest | P0 | COMPLETE | Bàn giao asset manifest hoặc mapping View → compiled asset | 01_DOCS/18_BUILD_AND_ASSET_PIPELINE.docx, Gruntfile.js, package.json
52 | BLD-P1-005 | Build validation | P1 | COMPLETE | Bàn giao build verification checklist/script | 01_DOCS/18_BUILD_AND_ASSET_PIPELINE.docx, Gruntfile.js, package.json
53 | BLD-P1-006 | Generated versus source assets | P1 | COMPLETE | Bàn giao danh sách generated artifacts | 01_DOCS/18_BUILD_AND_ASSET_PIPELINE.docx, Gruntfile.js, package.json

## F. DEPLOYMENT (12 Hạng mục)
STT | Mã ID | Tên Hạng Mục | Mức Độ | Trạng Thái | Yêu Cầu Bàn Giao | Tài Liệu / Bằng Chứng Đáp Ứng
54 | DPL-P0-001 | Deployment runbook | P0 | COMPLETE | Bàn giao runbook từ server sạch đến ứng dụng hoạt động | 01_DOCS/03_DEPLOYMENT_GUIDE.docx, 01_DOCS/02_INSTALLATION_GUIDE.docx
55 | DPL-P0-002 | Server provisioning | P0 | COMPLETE | Bàn giao provisioning code hoặc cấu hình server chi tiết | 01_DOCS/03_DEPLOYMENT_GUIDE.docx, 01_DOCS/02_INSTALLATION_GUIDE.docx
56 | DPL-P0-003 | Web-server configuration | P0 | COMPLETE | Bàn giao config production đã chuẩn hóa | 01_DOCS/03_DEPLOYMENT_GUIDE.docx, 01_DOCS/02_INSTALLATION_GUIDE.docx
57 | DPL-P0-004 | Database deployment | P0 | COMPLETE | Bàn giao thứ tự restore, migration và verification | 01_DOCS/03_DEPLOYMENT_GUIDE.docx, 01_DOCS/02_INSTALLATION_GUIDE.docx
58 | DPL-P0-005 | Storage deployment | P0 | COMPLETE | Bàn giao storage layout, mount, owner và backup policy | 01_DOCS/03_DEPLOYMENT_GUIDE.docx, 01_DOCS/02_INSTALLATION_GUIDE.docx
59 | DPL-P0-006 | Deployment secret injection | P0 | COMPLETE | Bàn giao secret injection process | 01_DOCS/03_DEPLOYMENT_GUIDE.docx, 01_DOCS/02_INSTALLATION_GUIDE.docx
60 | DPL-P0-007 | Health check | P0 | COMPLETE | Bàn giao health/smoke checklist | 01_DOCS/03_DEPLOYMENT_GUIDE.docx, 01_DOCS/02_INSTALLATION_GUIDE.docx
61 | DPL-P0-008 | Rollback procedure | P0 | COMPLETE | Bàn giao rollback runbook | 01_DOCS/03_DEPLOYMENT_GUIDE.docx, 01_DOCS/02_INSTALLATION_GUIDE.docx
62 | DPL-P0-009 | Production deployment record | P0 | COMPLETE | Bàn giao deployment record của production hiện tại | 01_DOCS/03_DEPLOYMENT_GUIDE.docx, 01_DOCS/02_INSTALLATION_GUIDE.docx
63 | DPL-P1-010 | CI/CD pipeline | P1 | COMPLETE | Bàn giao pipeline hiện dùng hoặc tài liệu quy trình tương đương | 01_DOCS/03_DEPLOYMENT_GUIDE.docx, 01_DOCS/02_INSTALLATION_GUIDE.docx
64 | DPL-P1-011 | Monitoring/alerting | P1 | COMPLETE | Bàn giao monitoring matrix và alert routing | 01_DOCS/03_DEPLOYMENT_GUIDE.docx, 01_DOCS/02_INSTALLATION_GUIDE.docx
65 | DPL-P1-012 | Capacity requirement | P1 | COMPLETE | Bàn giao sizing production và DEV/UAT | 01_DOCS/03_DEPLOYMENT_GUIDE.docx, 01_DOCS/02_INSTALLATION_GUIDE.docx

## G. SECURITY _ CREDENTIAL (14 H
STT | Mã ID | Tên Hạng Mục | Mức Độ | Trạng Thái | Yêu Cầu Bàn Giao | Tài Liệu / Bằng Chứng Đáp Ứng
66 | SEC-P0-001 | Database credential | P0 | COMPLETE | Rotate credential và cung cấp xác nhận thu hồi credential cũ | 02_SECURITY_AND_SOURCE/reports/SECURITY_AUDIT_REPORT.docx, 01_DOCS/07_CONFIG_REFERENCE.docx
67 | SEC-P0-002 | Application encryption key | P0 | COMPLETE | Cung cấp kế hoạch xử lý key, phạm vi dữ liệu bị ảnh hưởng và xác nhận key management | 02_SECURITY_AND_SOURCE/reports/SECURITY_AUDIT_REPORT.docx, 01_DOCS/07_CONFIG_REFERENCE.docx
68 | SEC-P0-003 | REST API key | P0 | COMPLETE | Thu hồi/rotate API key và bàn giao cách cấp key mới | 02_SECURITY_AND_SOURCE/reports/SECURITY_AUDIT_REPORT.docx, 01_DOCS/07_CONFIG_REFERENCE.docx
69 | SEC-P0-004 | Secret trong Primary SQL | P0 | COMPLETE | Bàn giao secret inventory và xác nhận rotate/revoke | 02_SECURITY_AND_SOURCE/reports/SECURITY_AUDIT_REPORT.docx, 01_DOCS/07_CONFIG_REFERENCE.docx
70 | SEC-P0-005 | SMTP credential | P0 | COMPLETE | Rotate SMTP credential và bàn giao cấu hình qua kênh an toàn | 02_SECURITY_AND_SOURCE/reports/SECURITY_AUDIT_REPORT.docx, 01_DOCS/07_CONFIG_REFERENCE.docx
71 | SEC-P0-006 | Zalo/OneSignal/notification token | P0 | COMPLETE | Rotate/revoke và cung cấp ownership/integration documentation | 02_SECURITY_AND_SOURCE/reports/SECURITY_AUDIT_REPORT.docx, 01_DOCS/07_CONFIG_REFERENCE.docx
72 | SEC-P0-007 | Secret manager | P0 | COMPLETE | Bàn giao secret management process | 02_SECURITY_AND_SOURCE/reports/SECURITY_AUDIT_REPORT.docx, 01_DOCS/07_CONFIG_REFERENCE.docx
73 | SEC-P0-008 | Primary SQL sanitization | P0 | COMPLETE | Bàn giao bản dữ liệu DEV/UAT đã ẩn danh hoặc quy trình cấp dữ liệu hợp pháp | 02_SECURITY_AND_SOURCE/reports/SECURITY_AUDIT_REPORT.docx, 01_DOCS/07_CONFIG_REFERENCE.docx
74 | SEC-P0-009 | Upload/media data privacy | P0 | COMPLETE | Bàn giao data classification, authorization và sanitized package | 02_SECURITY_AND_SOURCE/reports/SECURITY_AUDIT_REPORT.docx, 01_DOCS/07_CONFIG_REFERENCE.docx
75 | SEC-P0-010 | API authorization review | P0 | COMPLETE | Bàn giao API security matrix và kết quả kiểm thử authorization | 02_SECURITY_AND_SOURCE/reports/SECURITY_AUDIT_REPORT.docx, 01_DOCS/07_CONFIG_REFERENCE.docx
76 | SEC-P1-011 | Security audit report | P1 | COMPLETE | Bàn giao security assessment gần nhất | 02_SECURITY_AND_SOURCE/reports/SECURITY_AUDIT_REPORT.docx, 01_DOCS/07_CONFIG_REFERENCE.docx
77 | SEC-P1-012 | Secret scanning report | P1 | COMPLETE | Bàn giao secret scanning report | 02_SECURITY_AND_SOURCE/reports/SECURITY_AUDIT_REPORT.docx, 01_DOCS/07_CONFIG_REFERENCE.docx
78 | SEC-P1-013 | Access handover matrix | P1 | COMPLETE | Bàn giao access inventory qua kênh an toàn | 02_SECURITY_AND_SOURCE/reports/SECURITY_AUDIT_REPORT.docx, 01_DOCS/07_CONFIG_REFERENCE.docx
79 | SEC-P1-014 | Data retention/security policy | P1 | COMPLETE | Bàn giao security/data retention policy | 02_SECURITY_AND_SOURCE/reports/SECURITY_AUDIT_REPORT.docx, 01_DOCS/07_CONFIG_REFERENCE.docx

## H. API _ INTEGRATION (13 Hạng
STT | Mã ID | Tên Hạng Mục | Mức Độ | Trạng Thái | Yêu Cầu Bàn Giao | Tài Liệu / Bằng Chứng Đáp Ứng
80 | API-P0-001 | API inventory | P0 | COMPLETE | Bàn giao API inventory | 01_DOCS/10_API_INTEGRATION_GUIDE.docx, 01_DOCS/20_API_COLLECTION_GUIDE.docx, 01_DOCS/20_OPENAPI_POSTMAN_SPECIFICATION.json
81 | API-P0-002 | API contract | P0 | COMPLETE | Bàn giao OpenAPI hoặc Postman collection cập nhật | 01_DOCS/10_API_INTEGRATION_GUIDE.docx, 01_DOCS/20_API_COLLECTION_GUIDE.docx, 01_DOCS/20_OPENAPI_POSTMAN_SPECIFICATION.json
82 | API-P0-003 | API authentication | P0 | COMPLETE | Bàn giao authentication flow và key lifecycle | 01_DOCS/10_API_INTEGRATION_GUIDE.docx, 01_DOCS/20_API_COLLECTION_GUIDE.docx, 01_DOCS/20_OPENAPI_POSTMAN_SPECIFICATION.json
83 | API-P0-004 | API permission | P0 | COMPLETE | Bàn giao permission matrix | 01_DOCS/10_API_INTEGRATION_GUIDE.docx, 01_DOCS/20_API_COLLECTION_GUIDE.docx, 01_DOCS/20_OPENAPI_POSTMAN_SPECIFICATION.json
84 | API-P0-005 | API database dependency | P0 | COMPLETE | Bàn giao dependency mapping | 01_DOCS/10_API_INTEGRATION_GUIDE.docx, 01_DOCS/20_API_COLLECTION_GUIDE.docx, 01_DOCS/20_OPENAPI_POSTMAN_SPECIFICATION.json
85 | API-P0-006 | Integration inventory | P0 | COMPLETE | Bàn giao integration register | 01_DOCS/10_API_INTEGRATION_GUIDE.docx, 01_DOCS/20_API_COLLECTION_GUIDE.docx, 01_DOCS/20_OPENAPI_POSTMAN_SPECIFICATION.json
86 | API-P0-007 | Integration configuration | P0 | COMPLETE | Bàn giao config guide từng integration | 01_DOCS/10_API_INTEGRATION_GUIDE.docx, 01_DOCS/20_API_COLLECTION_GUIDE.docx, 01_DOCS/20_OPENAPI_POSTMAN_SPECIFICATION.json
87 | API-P0-008 | Integration test | P0 | COMPLETE | Bàn giao test evidence từng integration active | 01_DOCS/10_API_INTEGRATION_GUIDE.docx, 01_DOCS/20_API_COLLECTION_GUIDE.docx, 01_DOCS/20_OPENAPI_POSTMAN_SPECIFICATION.json
88 | API-P0-009 | Socket service | P0 | COMPLETE | Bàn giao source hoặc tài liệu service, endpoint và deployment ownership | 01_DOCS/10_API_INTEGRATION_GUIDE.docx, 01_DOCS/20_API_COLLECTION_GUIDE.docx, 01_DOCS/20_OPENAPI_POSTMAN_SPECIFICATION.json
89 | API-P0-010 | Payment integration | P0 | COMPLETE | Bàn giao danh sách gateway active, config và test mode procedure | 01_DOCS/10_API_INTEGRATION_GUIDE.docx, 01_DOCS/20_API_COLLECTION_GUIDE.docx, 01_DOCS/20_OPENAPI_POSTMAN_SPECIFICATION.json
90 | API-P1-011 | Rate limit/throttling | P1 | COMPLETE | Bàn giao rate-limit policy | 01_DOCS/10_API_INTEGRATION_GUIDE.docx, 01_DOCS/20_API_COLLECTION_GUIDE.docx, 01_DOCS/20_OPENAPI_POSTMAN_SPECIFICATION.json
91 | API-P1-012 | Webhook handling | P1 | COMPLETE | Bàn giao webhook register | 01_DOCS/10_API_INTEGRATION_GUIDE.docx, 01_DOCS/20_API_COLLECTION_GUIDE.docx, 01_DOCS/20_OPENAPI_POSTMAN_SPECIFICATION.json
92 | API-P1-013 | Integration failure handling | P1 | COMPLETE | Bàn giao operational runbook | 01_DOCS/10_API_INTEGRATION_GUIDE.docx, 01_DOCS/20_API_COLLECTION_GUIDE.docx, 01_DOCS/20_OPENAPI_POSTMAN_SPECIFICATION.json

## I. ROLE _ PERMISSION (9 Hạng m
STT | Mã ID | Tên Hạng Mục | Mức Độ | Trạng Thái | Yêu Cầu Bàn Giao | Tài Liệu / Bằng Chứng Đáp Ứng
93 | PER-P0-001 | Role inventory | P0 | COMPLETE | Bàn giao Role inventory đang áp dụng | 01_DOCS/08_ROLE_PERMISSION_GUIDE.docx, 03_MENU_ROUTES_DATABASE/reports/MENU_ROUTE_AUDIT_REPORT.docx
94 | PER-P0-002 | Permission inventory | P0 | COMPLETE | Bàn giao permission catalogue | 01_DOCS/08_ROLE_PERMISSION_GUIDE.docx, 03_MENU_ROUTES_DATABASE/reports/MENU_ROUTE_AUDIT_REPORT.docx
95 | PER-P0-003 | Module–Role–Permission matrix | P0 | COMPLETE | Bàn giao ma trận chính thức | 01_DOCS/08_ROLE_PERMISSION_GUIDE.docx, 03_MENU_ROUTES_DATABASE/reports/MENU_ROUTE_AUDIT_REPORT.docx
96 | PER-P0-004 | Menu permission | P0 | COMPLETE | Bàn giao menu permission mapping và test result | 01_DOCS/08_ROLE_PERMISSION_GUIDE.docx, 03_MENU_ROUTES_DATABASE/reports/MENU_ROUTE_AUDIT_REPORT.docx
97 | PER-P0-005 | Controller/API authorization | P0 | COMPLETE | Bàn giao authorization coverage report | 01_DOCS/08_ROLE_PERMISSION_GUIDE.docx, 03_MENU_ROUTES_DATABASE/reports/MENU_ROUTE_AUDIT_REPORT.docx
98 | PER-P0-006 | Admin account handover | P0 | COMPLETE | Bàn giao quy trình quản lý admin | 01_DOCS/08_ROLE_PERMISSION_GUIDE.docx, 03_MENU_ROUTES_DATABASE/reports/MENU_ROUTE_AUDIT_REPORT.docx
99 | PER-P1-007 | Segregation of Duties | P1 | COMPLETE | Bàn giao SoD matrix | 01_DOCS/08_ROLE_PERMISSION_GUIDE.docx, 03_MENU_ROUTES_DATABASE/reports/MENU_ROUTE_AUDIT_REPORT.docx
100 | PER-P1-008 | Permission test cases | P1 | COMPLETE | Bàn giao test cases và kết quả | 01_DOCS/08_ROLE_PERMISSION_GUIDE.docx, 03_MENU_ROUTES_DATABASE/reports/MENU_ROUTE_AUDIT_REPORT.docx
101 | PER-P1-009 | Permission audit log | P1 | COMPLETE | Bàn giao audit behavior và test evidence | 01_DOCS/08_ROLE_PERMISSION_GUIDE.docx, 03_MENU_ROUTES_DATABASE/reports/MENU_ROUTE_AUDIT_REPORT.docx

## J. WORKFLOW (10 Hạng mục)
STT | Mã ID | Tên Hạng Mục | Mức Độ | Trạng Thái | Yêu Cầu Bàn Giao | Tài Liệu / Bằng Chứng Đáp Ứng
102 | WF-P0-001 | Workflow catalogue | P0 | COMPLETE | Bàn giao Workflow catalogue theo Module | 01_DOCS/09_WORKFLOW_APPROVAL_GUIDE.docx, 01_DOCS/14_MODULE_CATALOGUE.docx
103 | WF-P0-002 | Rule catalogue | P0 | COMPLETE | Bàn giao Rule catalogue đã xác nhận | 01_DOCS/09_WORKFLOW_APPROVAL_GUIDE.docx, 01_DOCS/14_MODULE_CATALOGUE.docx
104 | WF-P0-003 | Master Data catalogue | P0 | COMPLETE | Bàn giao Master Data catalogue | 01_DOCS/09_WORKFLOW_APPROVAL_GUIDE.docx, 01_DOCS/14_MODULE_CATALOGUE.docx
105 | WF-P0-004 | Workflow ↔ Source mapping | P0 | COMPLETE | Bàn giao technical workflow mapping | 01_DOCS/09_WORKFLOW_APPROVAL_GUIDE.docx, 01_DOCS/14_MODULE_CATALOGUE.docx
106 | WF-P0-005 | Workflow status definition | P0 | COMPLETE | Bàn giao status/state dictionary | 01_DOCS/09_WORKFLOW_APPROVAL_GUIDE.docx, 01_DOCS/14_MODULE_CATALOGUE.docx
107 | WF-P0-006 | Approval workflow | P0 | COMPLETE | Bàn giao approval matrix | 01_DOCS/09_WORKFLOW_APPROVAL_GUIDE.docx, 01_DOCS/14_MODULE_CATALOGUE.docx
108 | WF-P0-007 | Workflow smoke/UAT tests | P0 | COMPLETE | Bàn giao test cases và test result | 01_DOCS/09_WORKFLOW_APPROVAL_GUIDE.docx, 01_DOCS/14_MODULE_CATALOGUE.docx
109 | WF-P1-008 | Exception/rollback workflow | P1 | COMPLETE | Bàn giao exception flow | 01_DOCS/09_WORKFLOW_APPROVAL_GUIDE.docx, 01_DOCS/14_MODULE_CATALOGUE.docx
110 | WF-P1-009 | Audit log coverage | P1 | COMPLETE | Bàn giao audit coverage matrix | 01_DOCS/09_WORKFLOW_APPROVAL_GUIDE.docx, 01_DOCS/14_MODULE_CATALOGUE.docx
111 | WF-P1-010 | KPI/report dependency | P1 | COMPLETE | Bàn giao KPI/report data lineage | 01_DOCS/09_WORKFLOW_APPROVAL_GUIDE.docx, 01_DOCS/14_MODULE_CATALOGUE.docx

## K. CRON _ JOB (9 Hạng mục)
STT | Mã ID | Tên Hạng Mục | Mức Độ | Trạng Thái | Yêu Cầu Bàn Giao | Tài Liệu / Bằng Chứng Đáp Ứng
112 | CRN-P0-001 | Cron inventory | P0 | COMPLETE | Bàn giao inventory toàn bộ cron/job | 04_OPERATIONS_AND_BACKUP/cron/cron_cli_runner.php, 04_OPERATIONS_AND_BACKUP/cron/crontab_linux.sample, 01_DOCS/11_OPERATIONAL_RUNBOOK.docx
113 | CRN-P0-002 | Cron schedule | P0 | COMPLETE | Bàn giao crontab hoặc scheduler manifest | 04_OPERATIONS_AND_BACKUP/cron/cron_cli_runner.php, 04_OPERATIONS_AND_BACKUP/cron/crontab_linux.sample, 01_DOCS/11_OPERATIONAL_RUNBOOK.docx
114 | CRN-P0-003 | Cron authentication/key | P0 | COMPLETE | Bàn giao cron key management | 04_OPERATIONS_AND_BACKUP/cron/cron_cli_runner.php, 04_OPERATIONS_AND_BACKUP/cron/crontab_linux.sample, 01_DOCS/11_OPERATIONAL_RUNBOOK.docx
115 | CRN-P0-004 | Cron dependency | P0 | COMPLETE | Bàn giao dependency và execution order | 04_OPERATIONS_AND_BACKUP/cron/cron_cli_runner.php, 04_OPERATIONS_AND_BACKUP/cron/crontab_linux.sample, 01_DOCS/11_OPERATIONAL_RUNBOOK.docx
116 | CRN-P0-005 | Cron monitoring | P0 | COMPLETE | Bàn giao monitoring và alert rule | 04_OPERATIONS_AND_BACKUP/cron/cron_cli_runner.php, 04_OPERATIONS_AND_BACKUP/cron/crontab_linux.sample, 01_DOCS/11_OPERATIONAL_RUNBOOK.docx
117 | CRN-P0-006 | Cron concurrency/lock | P0 | COMPLETE | Bàn giao locking behavior và recovery procedure | 04_OPERATIONS_AND_BACKUP/cron/cron_cli_runner.php, 04_OPERATIONS_AND_BACKUP/cron/crontab_linux.sample, 01_DOCS/11_OPERATIONAL_RUNBOOK.docx
118 | CRN-P0-007 | Cron test evidence | P0 | COMPLETE | Bàn giao execution log/test result | 04_OPERATIONS_AND_BACKUP/cron/cron_cli_runner.php, 04_OPERATIONS_AND_BACKUP/cron/crontab_linux.sample, 01_DOCS/11_OPERATIONAL_RUNBOOK.docx
119 | CRN-P1-008 | Retry/idempotency | P1 | COMPLETE | Bàn giao retry/idempotency matrix | 04_OPERATIONS_AND_BACKUP/cron/cron_cli_runner.php, 04_OPERATIONS_AND_BACKUP/cron/crontab_linux.sample, 01_DOCS/11_OPERATIONAL_RUNBOOK.docx
120 | CRN-P1-009 | Job failure recovery | P1 | COMPLETE | Bàn giao recovery procedure | 04_OPERATIONS_AND_BACKUP/cron/cron_cli_runner.php, 04_OPERATIONS_AND_BACKUP/cron/crontab_linux.sample, 01_DOCS/11_OPERATIONAL_RUNBOOK.docx

## L. BACKUP _ RESTORE (12 Hạng m
STT | Mã ID | Tên Hạng Mục | Mức Độ | Trạng Thái | Yêu Cầu Bàn Giao | Tài Liệu / Bằng Chứng Đáp Ứng
121 | BKR-P0-001 | Backup architecture | P0 | COMPLETE | Bàn giao kiến trúc backup thực tế | 04_OPERATIONS_AND_BACKUP/backup/backup_database.ps1, 04_OPERATIONS_AND_BACKUP/backup/backup_database.sh, 04_OPERATIONS_AND_BACKUP/backup/RESTORE_AND_ROLLBACK_DRILL.docx, 01_DOCS/19_DISASTER_RECOVERY_AND_RPO_RTO.docx
122 | BKR-P0-002 | Backup configuration | P0 | COMPLETE | Bàn giao config template và secret mechanism | 04_OPERATIONS_AND_BACKUP/backup/backup_database.ps1, 04_OPERATIONS_AND_BACKUP/backup/backup_database.sh, 04_OPERATIONS_AND_BACKUP/backup/RESTORE_AND_ROLLBACK_DRILL.docx, 01_DOCS/19_DISASTER_RECOVERY_AND_RPO_RTO.docx
123 | BKR-P0-003 | Backup schedule | P0 | COMPLETE | Bàn giao lịch backup | 04_OPERATIONS_AND_BACKUP/backup/backup_database.ps1, 04_OPERATIONS_AND_BACKUP/backup/backup_database.sh, 04_OPERATIONS_AND_BACKUP/backup/RESTORE_AND_ROLLBACK_DRILL.docx, 01_DOCS/19_DISASTER_RECOVERY_AND_RPO_RTO.docx
124 | BKR-P0-004 | Backup scope | P0 | COMPLETE | Bàn giao scope matrix | 04_OPERATIONS_AND_BACKUP/backup/backup_database.ps1, 04_OPERATIONS_AND_BACKUP/backup/backup_database.sh, 04_OPERATIONS_AND_BACKUP/backup/RESTORE_AND_ROLLBACK_DRILL.docx, 01_DOCS/19_DISASTER_RECOVERY_AND_RPO_RTO.docx
125 | BKR-P0-005 | Backup retention | P0 | COMPLETE | Bàn giao retention policy | 04_OPERATIONS_AND_BACKUP/backup/backup_database.ps1, 04_OPERATIONS_AND_BACKUP/backup/backup_database.sh, 04_OPERATIONS_AND_BACKUP/backup/RESTORE_AND_ROLLBACK_DRILL.docx, 01_DOCS/19_DISASTER_RECOVERY_AND_RPO_RTO.docx
126 | BKR-P0-006 | Backup encryption | P0 | COMPLETE | Bàn giao encryption/key management | 04_OPERATIONS_AND_BACKUP/backup/backup_database.ps1, 04_OPERATIONS_AND_BACKUP/backup/backup_database.sh, 04_OPERATIONS_AND_BACKUP/backup/RESTORE_AND_ROLLBACK_DRILL.docx, 01_DOCS/19_DISASTER_RECOVERY_AND_RPO_RTO.docx
127 | BKR-P0-007 | Restore test | P0 | COMPLETE | Bàn giao restore drill gần nhất hoặc thực hiện trên UAT | 04_OPERATIONS_AND_BACKUP/backup/backup_database.ps1, 04_OPERATIONS_AND_BACKUP/backup/backup_database.sh, 04_OPERATIONS_AND_BACKUP/backup/RESTORE_AND_ROLLBACK_DRILL.docx, 01_DOCS/19_DISASTER_RECOVERY_AND_RPO_RTO.docx
128 | BKR-P0-008 | Recovery Point Objective | P0 | COMPLETE | Bàn giao RPO được phê duyệt | 04_OPERATIONS_AND_BACKUP/backup/backup_database.ps1, 04_OPERATIONS_AND_BACKUP/backup/backup_database.sh, 04_OPERATIONS_AND_BACKUP/backup/RESTORE_AND_ROLLBACK_DRILL.docx, 01_DOCS/19_DISASTER_RECOVERY_AND_RPO_RTO.docx
129 | BKR-P0-009 | Recovery Time Objective | P0 | COMPLETE | Bàn giao RTO được phê duyệt | 04_OPERATIONS_AND_BACKUP/backup/backup_database.ps1, 04_OPERATIONS_AND_BACKUP/backup/backup_database.sh, 04_OPERATIONS_AND_BACKUP/backup/RESTORE_AND_ROLLBACK_DRILL.docx, 01_DOCS/19_DISASTER_RECOVERY_AND_RPO_RTO.docx
130 | BKR-P0-010 | Rollback database | P0 | COMPLETE | Bàn giao DB rollback procedure | 04_OPERATIONS_AND_BACKUP/backup/backup_database.ps1, 04_OPERATIONS_AND_BACKUP/backup/backup_database.sh, 04_OPERATIONS_AND_BACKUP/backup/RESTORE_AND_ROLLBACK_DRILL.docx, 01_DOCS/19_DISASTER_RECOVERY_AND_RPO_RTO.docx
131 | BKR-P1-011 | Disaster recovery | P1 | COMPLETE | Bàn giao DR plan | 04_OPERATIONS_AND_BACKUP/backup/backup_database.ps1, 04_OPERATIONS_AND_BACKUP/backup/backup_database.sh, 04_OPERATIONS_AND_BACKUP/backup/RESTORE_AND_ROLLBACK_DRILL.docx, 01_DOCS/19_DISASTER_RECOVERY_AND_RPO_RTO.docx
132 | BKR-P1-012 | Backup monitoring | P1 | COMPLETE | Bàn giao alert/verification process | 04_OPERATIONS_AND_BACKUP/backup/backup_database.ps1, 04_OPERATIONS_AND_BACKUP/backup/backup_database.sh, 04_OPERATIONS_AND_BACKUP/backup/RESTORE_AND_ROLLBACK_DRILL.docx, 01_DOCS/19_DISASTER_RECOVERY_AND_RPO_RTO.docx

## M. DOCUMENTATION (19 Hạng mục)
STT | Mã ID | Tên Hạng Mục | Mức Độ | Trạng Thái | Yêu Cầu Bàn Giao | Tài Liệu / Bằng Chứng Đáp Ứng
133 | DOC-P0-001 | README | P0 | COMPLETE | Bàn giao README của release | 01_DOCS/00_MASTER_INDEX.docx (Bao gồm đầy đủ 20 tài liệu kỹ thuật chuyên đề, Module Catalogue, UAT Checklist, Runbooks)
134 | DOC-P0-002 | Installation guide | P0 | COMPLETE | Bàn giao INSTALL guide | 01_DOCS/00_MASTER_INDEX.docx (Bao gồm đầy đủ 20 tài liệu kỹ thuật chuyên đề, Module Catalogue, UAT Checklist, Runbooks)
135 | DOC-P0-003 | Deployment guide | P0 | COMPLETE | Bàn giao deployment guide | 01_DOCS/00_MASTER_INDEX.docx (Bao gồm đầy đủ 20 tài liệu kỹ thuật chuyên đề, Module Catalogue, UAT Checklist, Runbooks)
136 | DOC-P0-004 | Database guide | P0 | COMPLETE | Bàn giao database runbook | 01_DOCS/00_MASTER_INDEX.docx (Bao gồm đầy đủ 20 tài liệu kỹ thuật chuyên đề, Module Catalogue, UAT Checklist, Runbooks)
137 | DOC-P0-005 | Environment/config guide | P0 | COMPLETE | Bàn giao config reference | 01_DOCS/00_MASTER_INDEX.docx (Bao gồm đầy đủ 20 tài liệu kỹ thuật chuyên đề, Module Catalogue, UAT Checklist, Runbooks)
138 | DOC-P0-006 | Module catalogue | P0 | COMPLETE | Bàn giao Module catalogue | 01_DOCS/00_MASTER_INDEX.docx (Bao gồm đầy đủ 20 tài liệu kỹ thuật chuyên đề, Module Catalogue, UAT Checklist, Runbooks)
139 | DOC-P0-007 | Architecture document | P0 | COMPLETE | Bàn giao architecture document | 01_DOCS/00_MASTER_INDEX.docx (Bao gồm đầy đủ 20 tài liệu kỹ thuật chuyên đề, Module Catalogue, UAT Checklist, Runbooks)
140 | DOC-P0-008 | Operational runbook | P0 | COMPLETE | Bàn giao runbook vận hành | 01_DOCS/00_MASTER_INDEX.docx (Bao gồm đầy đủ 20 tài liệu kỹ thuật chuyên đề, Module Catalogue, UAT Checklist, Runbooks)
141 | DOC-P0-009 | UAT checklist | P0 | COMPLETE | Bàn giao UAT checklist và kết quả gần nhất | 01_DOCS/00_MASTER_INDEX.docx (Bao gồm đầy đủ 20 tài liệu kỹ thuật chuyên đề, Module Catalogue, UAT Checklist, Runbooks)
142 | DOC-P0-010 | Release notes | P0 | COMPLETE | Bàn giao release notes | 01_DOCS/00_MASTER_INDEX.docx (Bao gồm đầy đủ 20 tài liệu kỹ thuật chuyên đề, Module Catalogue, UAT Checklist, Runbooks)
143 | DOC-P1-011 | API documentation | P1 | COMPLETE | Bàn giao OpenAPI/Postman và guide | 01_DOCS/00_MASTER_INDEX.docx (Bao gồm đầy đủ 20 tài liệu kỹ thuật chuyên đề, Module Catalogue, UAT Checklist, Runbooks)
144 | DOC-P1-012 | Data dictionary/ERD | P1 | COMPLETE | Bàn giao data dictionary và ERD | 01_DOCS/00_MASTER_INDEX.docx (Bao gồm đầy đủ 20 tài liệu kỹ thuật chuyên đề, Module Catalogue, UAT Checklist, Runbooks)
145 | DOC-P1-013 | Role/Permission guide | P1 | COMPLETE | Bàn giao permission guide | 01_DOCS/00_MASTER_INDEX.docx (Bao gồm đầy đủ 20 tài liệu kỹ thuật chuyên đề, Module Catalogue, UAT Checklist, Runbooks)
146 | DOC-P1-014 | Workflow/Rule guide | P1 | COMPLETE | Bàn giao tài liệu được owner xác nhận | 01_DOCS/00_MASTER_INDEX.docx (Bao gồm đầy đủ 20 tài liệu kỹ thuật chuyên đề, Module Catalogue, UAT Checklist, Runbooks)
147 | DOC-P1-015 | Integration guide | P1 | COMPLETE | Bàn giao integration runbook | 01_DOCS/00_MASTER_INDEX.docx (Bao gồm đầy đủ 20 tài liệu kỹ thuật chuyên đề, Module Catalogue, UAT Checklist, Runbooks)
148 | DOC-P1-016 | Troubleshooting guide | P1 | COMPLETE | Bàn giao troubleshooting guide | 01_DOCS/00_MASTER_INDEX.docx (Bao gồm đầy đủ 20 tài liệu kỹ thuật chuyên đề, Module Catalogue, UAT Checklist, Runbooks)
149 | DOC-P1-017 | Monitoring/logging guide | P1 | COMPLETE | Bàn giao observability guide | 01_DOCS/00_MASTER_INDEX.docx (Bao gồm đầy đủ 20 tài liệu kỹ thuật chuyên đề, Module Catalogue, UAT Checklist, Runbooks)
150 | DOC-P1-018 | Maintenance guide | P1 | COMPLETE | Bàn giao maintenance guide | 01_DOCS/00_MASTER_INDEX.docx (Bao gồm đầy đủ 20 tài liệu kỹ thuật chuyên đề, Module Catalogue, UAT Checklist, Runbooks)
151 | DOC-P1-019 | Handover contact/escalation | P1 | COMPLETE | Bàn giao contact/escalation matrix | 01_DOCS/00_MASTER_INDEX.docx (Bao gồm đầy đủ 20 tài liệu kỹ thuật chuyên đề, Module Catalogue, UAT Checklist, Runbooks)